## Action_Log
Action Item | Priority | Owner | Action Date | Due Date | Status | Notes
How to Develop paddlers - transition from Docks to other venues (rivers, canals, sea, etc) | None | ??? | 2023-01-18 |  | Unknown
Organise & co-ordinate ‘Sea Leader Team’ to put on more trips | None | Ian Bell | 2023-01-18 |  | Unknown
Progress members to SUP Leaders | None | Adya Misra | 2023-01-18 |  | Unknown
Determine state of Club’s SUPs and seek feasibility on purchase of new kit | None | Adya Misra | 2023-01-18 |  | Pending | Awaiting order of new SUPs. KS in communication with dealer of rigid boards.
Proposal for Internal Audit of Club Accounts | None | Andy Garland | 2023-01-18 |  | Unknown
Review ‘Sunday Social Paddle’ | None | Keith Steer | 2023-01-18 |  | Unknown
‘Virtual’ lock change on the Dock Compound | None | Keith Steer | 2023-01-18 | 2023-06-29 | Done | https://groups.google.com/g/lccstewardship/c/tqSy6VPJh5k
First Aid course provision for Leaders | None | Ian Bell | 2023-01-18 |  | Unknown
Each ‘Section’ to hold frequent mini-meetings | None | Discipline Co-ords | 2023-10-02 |  | Unknown
Review and provide draft update of a ‘Best Practice for Coordinators’ | None | Richard Clews | 2023-10-02 |  | Unknown
Check leader ratios and update website accordingly | None | Keith Steer | 2023-10-02 | 2021-05-17 | Done | https://groups.google.com/g/lccstewardship/c/i2CyfTbFcYY/m/IUuoZ2jtAwAJ
Create (or locate) a draft Club Trip email template for review | None | ??? | 2023-10-02 |  | Unknown
Email members to recruit new Group Leaders / Assistants (after AGM) | None | Roy McHale | 2023-10-02 |  | Unknown
Social Media usage… developing & testing? | None | ??? | 2023-10-02 | 2023-11-15 | Pending | https://groups.google.com/g/lccstewardship/c/OPH7tRY5iTk/m/cML94BYtDAAJ?utm_medium=email&utm_source=footer
First Aid course provision for Leaders | None | Ian Bell | 2023-01-18 |  | Unknown
Each ‘Section’ to hold frequent mini-meetings | None | Discipline Co-ords | 2023-10-02 |  | Unknown
Review and provide draft update of a ‘Best Practice for Coordinators’ | None | Richard Clews | 2023-10-02 |  | Unknown
Check leader ratios and update website accordingly | None | Keith Steer | 2023-10-02 | 2021-05-17 | Done | https://groups.google.com/g/lccstewardship/c/i2CyfTbFcYY/m/IUuoZ2jtAwAJ
Create (or locate) a draft Club Trip email template for review | None | ??? | 2023-10-02 |  | Unknown
Email members to recruit new Group Leaders / Assistants (after AGM) | None | Roy McHale | 2023-10-02 |  | Unknown
Social Media usage… developing & testing? Member communications?? | None | ??? | 2023-10-02 | 2023-11-15 | Pending | https://groups.google.com/g/lccstewardship/c/OPH7tRY5iTk/m/cML94BYtDAAJ?utm_medium=email&utm_source=footer
Implement a Coaches & Leaders discussion forum - WhatsApp, or similar? | None | ??? | 2023-10-02 | 2023-11-15 | Unknown | https://groups.google.com/g/lccstewardship/c/OPH7tRY5iTk/m/cML94BYtDAAJ?utm_medium=email&utm_source=footer
Draft Generic Sea & River Risk Assessments for review | None | Keith Steer & Ian Bell | 2023-10-02 | 2023-11-15 | Pending | http://liverpoolcanoeclub.co.uk/members/Club%20Documents/Risk%20Assessments/
Determine and draft implementation of ‘Friend or Family’ trial sessions | None | Richard Clews | 2023-10-23 |  | Unknown | Approved during AGM
Determine and draft constitution change for ‘Student Membership’ | None | Richard Clews | 2023-10-23 |  | Unknown | Approved during AGM Student membership is live on our join us page!
Draft a form that section leads can use to propose purchase of kit, as a way of investing club funds back into club | None | Richard Clews | 2023-11-15
Create and send a template for emails that can be used to advertise non club trips | None | Keith Steer | 2023-11-15
Check available instant access high interest savings accounts to understand if investing club funds is feasible | None | Craig Ford | 2023-11-15